## Overview
Project Name |  |  | 3D-Scanner
Current Project Week |  |  | 1
Project Type | PRO-2 |  | 4 |  | ECTS
Project Life Span |  |  | 12 |  | Weeks
Resulting Workload |  |  | 6000 |  | Minutes
|  |  | 100 |  | Hours
|  |  | ca. | 8.3333 | Hours per week
Current Overview | [5 empty] | Complete Overview
Week Nr. |  | 1 | Debit Hours (as planned) | Actual Hours | Difference | Week Overview | 06.11 - 12.11.2017 | 13.11 - 19.11.2017 | 20.11 - 26.11.2017 | 27.11 - 03.12.2017 | 04.12 - 10.12.2017 | 11.12 - 17.12.2017 | 18.12 - 24.12.2017 | 25.12 - 31.12.2017 | 01.01 - 07.01.2018 | 08.01 - 14.01.2018 | 15.01 - 21.01.2018 | 22.01 - 28.01.2018 | 29.01 - 04.02.2018 | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | DD.MM - DD.MM.YYYY | Sum | Debit Hours - Complete - | Difference - Complete -
[7 empty] | Week 01 | Week 02 | Week 03 | Week 04 | Week 05 | Week 06 | Week 07 | Week 08 | Week 09 | Week 10 | Week 11 | Week 12 | R-Week 13 | R-Week 14 | R-Week 15 | R-Week 16 | R-Week 17 | R-Week 18 | R-Week 19 | R-Week 20
Boris Fuchs |  |  | 0 | 3 | 3 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -30
[6 empty] | Actual | 3 | 6 | 6 | 6 | 1 | 2 | 1 | 32 | 0 | 2 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
[6 empty] | Difference | 3 | 6 | 6 | 6 | 1 | 2 | 1 | 32 | 0 | 2 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70
Paul Schmutz |  |  | 0 | 5 | 5 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | -19
[6 empty] | Actual | 5 | 6 | 2 | 4 | 1 | 2 | 1 | 32 | 0 | 2 | 16 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
[6 empty] | Difference | 5 | 6 | 2 | 4 | 1 | 2 | 1 | 32 | 0 | 2 | 16 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
---- |  |  | 0 | 0 | 0 | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Difference | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Std-A
Time Recording
Boris Fuchs
Week 01 |  |  |  | 06.11 - 12.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 | Meetings | 75 | Minutes
3 | Bauhaus | 120 | Minutes | Suchen nach Holzplatten, Dreibein usw.
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 3 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 13.11 - 19.11.2017
Nr | Type of Work | Duration |  | Comment
1 | Planung | 120 | Minutes
2 | Planung | 120 | Minutes
3 | Recherche | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 20.11 - 26.11.2017
Nr | Type of Work | Duration |  | Comment
1 | Bauhaus | 100 | Minutes | Suchen nach Holzplatten, Dreibein usw.
2 | Planung | 120 | Minutes
3 | Recherche | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 27.11 - 03.12.2017
Nr | Type of Work | Duration |  | Comment
1 | 3D Plan | 120 | Minutes
2 | Planung | 120 | Minutes
3 | Recherche | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 04.12 - 10.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Meeting | 30 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 11.12 - 17.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Bestellung Teile, Kostenplan | 100 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 2 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 18.12 - 24.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Abholung Bauteile | 30 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 25.12 - 31.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Umsetzung | 600 | Minutes
2 | Umsetzung | 600 | Minutes
3 | Umsetzung | 720 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 32 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 01.01 - 07.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 08.01 - 14.01.2018
Nr | Type of Work | Duration |  | Comment
1 | Programmierung | 120 | Minutes | Recherche Lego Brick Programmierung
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 2 | Hours
Geplant |  | 0 | Hours
Week11 |  |  |  | 15.01 - 21.01.2018
Nr | Type of Work | Duration |  | Comment
1 | Projektdokumentation | 60 | Minutes
2 | Programmierung Brick | 360 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 7 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 22.01 - 28.01.2018
Nr | Type of Work | Duration |  | Comment
1 | Programmierung Brick | 180 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 3 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | 29.01 - 04.02.2018
Nr | Type of Work | Duration |  | Comment
1 | 3D Scan Video | 60 | Minutes | Video für Präsentation aufnehmen
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-B
Time Recording
Paul Schmutz
Week 01 |  |  |  | 06.11 - 12.11.2017
Nr | Type of Work | Duration |  | Comment
1 | Protokoll, Aufbereitung Dokumente | 100 | Minutes | Meeting Protokoll 1, Dokumente vorbereiten, Repository erstellen
2 | Meetings | 75 | Minutes
3 | Recherche | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 5 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 13.11 - 19.11.2017
Nr | Type of Work | Duration |  | Comment
1 | Planung | 120 | Minutes
2 | Planung | 120 | Minutes
3 | Recherche | 120 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 20.11 - 26.11.2017
Nr | Type of Work | Duration |  | Comment
1 | Planung | 120 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 2 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 27.11 - 03.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Planung | 120 | Minutes
2 | Recherche | 120 | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 4 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 04.12 - 10.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Meeting | 30 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 11.12 - 17.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Bestellung Teile, Kostenplan | 100 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 2 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 18.12 - 24.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Abholung Bauteile | 30 | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 1 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 25.12 - 31.12.2017
Nr | Type of Work | Duration |  | Comment
1 | Umsetzung | 600 | Minutes
2 | Umsetzung | 600 | Minutes
3 | Umsetzung | 720 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 32 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 01.01 - 07.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 08.01 - 14.01.2018
Nr | Type of Work | Duration |  | Comment
1 | Programmierung | 120 | Minutes | Recherche Lego Brick Programmierung
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 2 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 15.01 - 21.01.2018
Nr | Type of Work | Duration |  | Comment
1 | Projektdokumentation | 60 | Minutes
2 | Programmierung Brick | 360 | Minutes
3 | Programmierung Brick | 300 | Minutes
4 | Programmierung Brick | 240 | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 16 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 22.01 - 28.01.2018
Nr | Type of Work | Duration |  | Comment
1 | Programmierung Brick | 240 | Minutes
2 | Programmierung Brick | 100 | Minutes | Eigenständiges Programm für Brick, Source Code dokumentieren
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 6 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | 29.01 - 04.02.2018
Nr | Type of Work | Duration |  | Comment
1 | 3D Scan Video | 60 | Minutes | Video für Präsentation aufnehmen
2 | Dokumentation | 120 | Minutes | Abstract, Präsentation (Videos, 3D Modelle)
3 | Dokumentation | 60 | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 4 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-C
Time Recording
----
Week 01 |  |  |  | 06.11 - 12.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 13.11 - 19.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 20.11 - 26.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 27.11 - 03.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 04.12 - 10.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 11.12 - 17.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 18.12 - 24.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 25.12 - 31.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 01.01 - 07.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 08.01 - 14.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 15.01 - 21.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 22.01 - 28.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | 29.01 - 04.02.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-D
Time Recording
----
Week 01 |  |  |  | 06.11 - 12.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 13.11 - 19.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 20.11 - 26.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 27.11 - 03.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 04.12 - 10.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 11.12 - 17.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 18.12 - 24.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 25.12 - 31.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 01.01 - 07.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 08.01 - 14.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 15.01 - 21.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 22.01 - 28.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | 29.01 - 04.02.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## Std-E
Time Recording
----
Week 01 |  |  |  | 06.11 - 12.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 02 |  |  |  | 13.11 - 19.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 03 |  |  |  | 20.11 - 26.11.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 04 |  |  |  | 27.11 - 03.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 05 |  |  |  | 04.12 - 10.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 06 |  |  |  | 11.12 - 17.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 07 |  |  |  | 18.12 - 24.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 08 |  |  |  | 25.12 - 31.12.2017
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 09 |  |  |  | 01.01 - 07.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 10 |  |  |  | 08.01 - 14.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 11 |  |  |  | 15.01 - 21.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
Week 12 |  |  |  | 22.01 - 28.01.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 13 |  |  |  | 29.01 - 04.02.2018
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 14 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 15 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 16 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 17 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 18 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 19 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours
RESERVE-Week 20 |  |  |  | DD.MM - DD.MM.YYYY
Nr | Type of Work | Duration |  | Comment
1 |  |  | Minutes
2 |  |  | Minutes
3 |  |  | Minutes
4 |  |  | Minutes
5 |  |  | Minutes
6 |  |  | Minutes
Sum |  | 0 | Hours
Geplant |  | 0 | Hours

## dynamic Data
Project Weeks
Week 1 | 06.11 - 12.11.2017
Week 2 | 13.11 - 19.11.2017
Week 3 | 20.11 - 26.11.2017
Week 4 | 27.11 - 03.12.2017
Week 5 | 04.12 - 10.12.2017
Week 6 | 11.12 - 17.12.2017
Week 7 | 18.12 - 24.12.2017
Week 8 | 25.12 - 31.12.2017
Week 9 | 01.01 - 07.01.2018
Week 10 | 08.01 - 14.01.2018
Week 11 | 15.01 - 21.01.2018
Week 12 | 22.01 - 28.01.2018
R-Week 13 | 29.01 - 04.02.2018
R-Week 14 | DD.MM - DD.MM.YYYY
R-Week 15 | DD.MM - DD.MM.YYYY
R-Week 16 | DD.MM - DD.MM.YYYY
R-Week 17 | DD.MM - DD.MM.YYYY
R-Week 18 | DD.MM - DD.MM.YYYY
R-Week 19 | DD.MM - DD.MM.YYYY
R-Week 20 | DD.MM - DD.MM.YYYY
Participantes
Std-A | Boris Fuchs
Std-B | Paul Schmutz
Std-C | ----
Std-D | ----
Std-E | ----
Project Types
PRO-1
PRO-2
PRO-3
PRO-4
PRO-2-M
PRO-3-M